## Backlog
ID | Use Case / Work Item | Module | Actor / Role | Lead / Reviewer | Status | Priority / Difficulty | Description
UC-01 | Register | Identity & Account Management | Guest / Email Service | Unassigned | Proposed | P0 / Medium | Visitor registers with unique email, receives verification token, and activates customer account upon email confirmation
UC-02 | Login | Identity & Account Management | Customer / Staff / Admin | Unassigned | Proposed | P0 / Medium | Active verified user receives a secure role-appropriate session and token
UC-03 | Logout | Identity & Account Management | Authenticated User | Unassigned | Proposed | P0 / Low | Current user session terminates and access tokens are invalidated
UC-04 | Manage Personal Profile & Addresses | Identity & Account Management | Customer | Unassigned | Proposed | P1 / Medium | Customer maintains personal contact profile and creates, edits, or defaults delivery addresses
UC-05 | Change Own Password | Identity & Account Management | Authenticated User | Unassigned | Proposed | P1 / Medium | Logged-in user replaces password after validating existing password credentials
UC-06 | Reset Forgotten Password | Identity & Account Management | Unauthenticated User / Email Service | Unassigned | Proposed | P1 / Medium | Account owner uses an expiring one-time email token to define a new password
UC-07 | Manage Accounts | Identity & Account Management | Admin / Email Service | Unassigned | Proposed | P1 / Medium | Admin creates, locks, unlocks accounts and issues setup credentials
UC-08 | Browse and Search Products | Product Discovery | Guest / Customer | Unassigned | Proposed | P0 / Medium | Visitor searches by keywords and filters active catalog by category, brand, price, and stock availability
UC-09 | View Product Detail | Product Discovery | Guest / Customer | Unassigned | Proposed | P0 / Low | Visitor views active product media, technical specifications, purchasable SKUs, pricing, and stock status
UC-10 | Manage Shopping Cart | Product Discovery | Customer | Unassigned | Proposed | P0 / Medium | Customer adds, updates quantities within available limits, or clears cart items
UC-11 | Manage Product Classification Data | Catalog & SKU Management | Admin | Unassigned | Proposed | P1 / Medium | Admin creates, updates, and deactivates product categories
UC-12 | Manage Brands | Catalog & SKU Management | Admin | Unassigned | Proposed | P1 / Medium | Admin creates, updates, and deactivates appliance brand reference entities
UC-13 | Manage Product Catalogue and SKUs | Catalog & SKU Management | Admin | Unassigned | Proposed | P0 / High | Admin defines products and manual SKU variants with list prices and minimum stock thresholds
UC-14 | Place Customer Order | Online Ordering | Customer | Unassigned | Proposed | P0 / High | System validates cart, reserves available stock, and creates pending COD or awaiting-payment order
UC-15 | Process Online Payment | Online Ordering | Customer / Payment Gateway | Unassigned | Proposed | P0 / High | Customer submits payment; system processes signed idempotent gateway callback to confirm or fail order
UC-16 | View Own Orders and Tracking | Online Ordering | Customer | Unassigned | Proposed | P0 / Medium | Customer inspects order history, live fulfillment timeline, payment receipts, and return progress
UC-17 | Cancel Eligible Own Order | Online Ordering | Customer / Payment Gateway | Unassigned | Proposed | P0 / High | Customer cancels unfulfilled order; system releases reserved stock and triggers online refund if prepaid
UC-18 | View and Search Sales Orders | Online Ordering | Staff / Admin | Unassigned | Proposed | P0 / Medium | Operator searches, filters, and inspects complete multi-channel order operational details
UC-19 | Confirm Sales Order | Online Ordering | Staff / Admin | Unassigned | Proposed | P0 / Medium | Operator validates customer and delivery details to transition order from pending to confirmed
UC-20 | Sell Products at Counter | Counter Sales | Staff / Admin | Unassigned | Proposed | P0 / High | Point-of-sale command completes instant sale, collection, direct physical stock deduction, and receipt printing
UC-21 | Fulfill and Dispatch Order | Fulfillment & Delivery | Staff / Admin | Unassigned | Proposed | P0 / High | Operator packs confirmed items and transitions stock from reserved to officially dispatched
UC-22 | Record Delivery Outcome | Fulfillment & Delivery | Staff / Admin | Unassigned | Proposed | P0 / High | Operator marks delivery as completed with COD settlement or failed with return-to-inventory processing
UC-23 | Cancel Order by Store | Fulfillment & Delivery | Admin / Payment Gateway | Unassigned | Proposed | P0 / High | Admin cancels order prior to dispatch with audit reason, releasing reserved stock and initiating refund
UC-24 | View Inventory Overview | Inventory Management | Staff / Admin | Unassigned | Proposed | P0 / Medium | Operator inspects on-hand, reserved, and available stock balances with low-stock warnings across SKUs
UC-25 | Adjust Stock | Inventory Management | Admin | Unassigned | Proposed | P0 / Medium | Admin enters reasoned physical audit count adjustments and logs immutable variance records
UC-26 | View Stock Movement History | Inventory Management | Admin | Unassigned | Proposed | P1 / Medium | Admin audits end-to-end ledger of physical, reservation, PO receipt, and adjustment transactions
UC-27 | Manage Suppliers | Purchasing | Admin | Unassigned | Proposed | P1 / Medium | Admin registers, edits, and manages appliance supplier directory details
UC-28 | Create Purchase Order | Purchasing | Admin | Unassigned | Proposed | P0 / Medium | Admin drafts and submits inbound restocking order with target supplier, SKUs, and purchase prices
UC-29 | Receive Stock against Purchase Order | Purchasing | Staff / Admin | Unassigned | Proposed | P0 / High | Staff verifies delivery against PO; system automatically increases physical stock balances and logs movements
UC-30 | Request Return for Own Order | Returns Processing | Customer | Unassigned | Proposed | P1 / High | Customer submits online return request for specific SKUs on delivered orders within return window
UC-31 | Create In-Store Return Request | Returns Processing | Staff / Admin | Unassigned | Proposed | P1 / High | Staff creates return request at counter upon inspecting physical purchase receipt and items
UC-32 | Inspect and Review Return Request | Returns Processing | Staff / Admin | Unassigned | Proposed | P1 / High | Staff evaluates physical item condition; Admin approves/rejects and restocks intact units to available inventory
UC-33 | Record Refund Completion | Returns Processing | Admin / Payment Gateway | Unassigned | Proposed | P1 / High | Admin executes and records online gateway refund or cash disbursement for approved return request
UC-34 | View Financial and Sales Reports | Reporting & Reconciliation | Admin | Unassigned | Proposed | P1 / High | Admin analyzes sales volume, revenue breakdown by channel (online vs counter), and cash inflows/outflows
UC-35 | View Inventory Roll-Forward Report | Reporting & Reconciliation | Admin | Unassigned | Proposed | P1 / High | Admin audits balance reconciliation matrix: opening stock + inbound POs - sales/shrinkage = closing stock

## Contribution
Name | Role | Tasks/Modules Assigned | Contribution % | Notes
ChuanDH | Member | hahaha | 20%
ThienTP | Leader | hahaha | 20%
AnNP | Member | hahaha | 20%
NhaLP | Member | hahaha | 20%
TranLTB | Member | hahaha | 20%

## Iter1
No | Screen / Function | Assigned To | UC ID | Start Date | End Date | Status | Commit Link | Notes
Iteration 1
1 | Register |  | UC-01 | 2026-09-21 | 2026-09-27 | To Do
2 | Login |  | UC-02 | 2026-09-21 | 2026-09-27 | To Do
3 | Logout |  | UC-03 | 2026-09-21 | 2026-09-27 | To Do
4 | Manage Personal Profile & Addresses |  | UC-04 | 2026-09-21 | 2026-09-27 | To Do
5 | Change Own Password |  | UC-05 | 2026-09-21 | 2026-09-27 | To Do
6 | Reset Forgotten Password |  | UC-06 | 2026-09-21 | 2026-09-27 | To Do
7 | Manage Accounts |  | UC-07 | 2026-09-21 | 2026-09-27 | To Do
8 | Browse and Search Products |  | UC-08 | 2026-09-21 | 2026-09-27 | To Do
9 | View Product Detail |  | UC-09 | 2026-09-21 | 2026-09-27 | To Do
10 | Manage Shopping Cart |  | UC-10 | 2026-09-21 | 2026-09-27 | To Do
11 | Manage Product Classification Data |  | UC-11 | 2026-09-21 | 2026-09-27 | To Do
12 | Manage Brands |  | UC-12 | 2026-09-21 | 2026-09-27 | To Do
13 | Manage Suppliers |  | UC-27 | 2026-09-21 | 2026-09-27 | To Do

## Iter2
No | Screen / Function | Assigned To | UC ID | Issue ID | Start Date | End Date | Status | Commit Link | Notes
Iteration 1
1 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
2 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
3 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
4 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
5 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
6 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
7 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
8 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
9 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
10 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
11 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
12 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
13 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
14 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
15 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
16 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
17 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
18 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
19 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
20 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
21 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
22 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
23 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
24 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
25 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
26 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
27 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
28 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
29 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
30 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done

## Iter3
No | Screen / Function | Assigned To | UC ID | Issue ID | Start Date | End Date | Status | Commit Link | Notes
Iteration 1
1 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
2 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
3 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
4 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
5 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
6 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
7 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
8 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
9 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
10 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
11 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
12 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
13 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
14 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
15 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
16 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
17 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
18 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
19 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
20 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
21 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
22 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
23 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
24 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
25 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
26 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
27 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
28 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
29 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
30 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done

## Iter4
No | Screen / Function | Assigned To | UC ID | Issue ID | Start Date | End Date | Status | Commit Link | Notes
Iteration 1
1 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
2 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
3 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
4 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
5 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
6 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
7 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
8 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
9 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
10 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
11 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
12 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
13 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
14 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
15 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
16 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
17 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
18 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
19 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
20 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
21 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
22 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
23 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
24 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
25 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
26 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
27 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
28 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
29 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done
30 |  |  |  |  | 2026-06-27 | 2026-07-04 | Done