## Backlog
ID | Module | Lead / Reviewer | Actor / Role | Use Case / Work Item | Status | Target Week | Priority / Difficulty | Description | Dependencies & Acceptance Evidence
UC-01 | Identity | A / B | Guest | Register Customer Account | Proposed | W3 | P0 / Medium / 2 pts | Visitor verifies email and receives an active Customer account | Dependencies: TECH-02, SMTP proof. Acceptance: valid/expired/reused/replaced token; ACTIVE login only. Backlog outcome: Verified Customer registration.
UC-02 | Identity | A / C | Customer/Staff/Manager | Login | Proposed | W2 | P0 / Medium / 2 pts | Active user receives a secure role-appropriate session | Dependencies: TECH-02, Manager seed. Acceptance: session rotation, state rejection, CSRF refresh, role navigation. Backlog outcome: Role-correct login session.
UC-03 | Identity | A / C | Authenticated User | Logout | Proposed | W2 | P0 / Low / 1 pts | Current session ends and protected APIs reject it | Dependencies: UC-02. Acceptance: POST+CSRF invalidates session; protected API becomes 401. Backlog outcome: Session logout.
UC-04 | Customer account | A / B | Customer | Manage Personal Profile | Proposed | W3 | P1 / Medium / 2 pts | Customer views and updates own allowed contact fields | Dependencies: UC-02. Acceptance: field validation and server-owned Customer identity isolation. Backlog outcome: Own Customer profile maintenance.
UC-05 | Customer account | A / C | Customer | Manage Delivery Addresses | Proposed | W3 | P0 / Medium / 2 pts | Customer creates, edits, selects default, and deactivates own addresses | Dependencies: UC-02. Acceptance: create/edit/default/deactivate; wrong-owner request is rejected. Backlog outcome: Own delivery-address maintenance.
UC-06 | Credential security | A / C | Authenticated User | Change Own Password | Proposed | W7 | P1 / Medium / 2 pts | User replaces password after proving the current password | Dependencies: UC-02. Acceptance: wrong current password rejected; all existing sessions invalidated. Backlog outcome: Own password replacement.
UC-07 | Credential recovery | A / B | Guest | Reset Forgotten Password | Proposed | W7 | P1 / Medium / 2 pts | Account owner uses a one-use expiring email token to replace password | Dependencies: SMTP proof. Acceptance: generic response; 30-minute, replacement, reuse, session tests. Backlog outcome: Forgotten-password recovery.
UC-08 | Staff administration | A / E | Manager | Manage Staff Accounts | Proposed | W7 | P1 / Medium / 2 pts | Manager creates/edits/activates/deactivates Staff and issues setup access | Dependencies: UC-02, SMTP proof. Acceptance: Staff-only target guard; setup/activate/deactivate/session behavior. Backlog outcome: Staff account lifecycle.
UC-09 | Product discovery | B / D | Guest/Customer | Browse and Search Products | Proposed | W3 | P0 / Medium / 2 pts | Visitor receives a paged active catalogue matching filters/sort/search | Dependencies: UC-19–20 seed. Acceptance: active filtering, bounded stable paging, search/sort, no N+1 evidence. Backlog outcome: Public catalogue/search.
UC-10 | Product discovery | B / D | Guest/Customer | View Product Detail | Proposed | W3 | P0 / Low / 1 pts | Visitor sees one active product, purchasable SKUs, price, and availability | Dependencies: UC-20. Acceptance: active visibility, availability, inactive/missing behavior. Backlog outcome: Public Product/SKU detail.
UC-11 | Shopping cart | B / A | Guest/Customer | Manage Shopping Cart | Proposed | W3 | P0 / Medium / 2 pts | Visitor adds, changes, removes, or clears browser-local SKU quantities | Dependencies: UC-09–10. Acceptance: add/update/remove/clear; corrupt/stale storage; server values untrusted. Backlog outcome: Browser-local cart.
UC-12 | Customer ordering | C / D | Customer | Place Customer Order | Proposed | W4 | P0 / High / 3 pts | Server revalidates address/price/stock/payment, reserves stock, snapshots sale, and creates one order | Dependencies: UC-05, UC-11, UC-20–21. Acceptance: rollback, stale price, last-unit race, exact retry/conflicting key. Backlog outcome: Atomic Customer order placement.
UC-13 | Online payment | C / A | Customer | Complete Online Payment | Proposed | W7 | P1 / High / 3 pts | One verified gateway result records collection once and confirms the pending order | Dependencies: UC-12, provider proof. Acceptance: bad signature/ref/amount, duplicate, expiry and late-success race. Backlog outcome: Verified idempotent online payment.
UC-14 | Customer enquiry | A / B | Customer | View My Order History | Proposed | W4 | P0 / Low / 1 pts | Customer sees only own orders with paging and filters | Dependencies: UC-12. Acceptance: mandatory owner predicate, status filter, deterministic paging. Backlog outcome: Owned paged order history.
UC-15 | Customer enquiry | B / A | Customer | View Own Order Detail and Receipt | Proposed | W4 | P0 / Medium / 2 pts | Customer sees owned order/payment/timeline/return state and paid receipt when eligible | Dependencies: UC-12–14. Acceptance: no cross-owner leakage; payment/return/actions and paid-only receipt. Backlog outcome: Owned order detail/timeline/receipt.
UC-16 | Customer cancellation | C / D | Customer | Cancel Eligible Own Order | Proposed | W7 | P0 / High / 3 pts | Eligible pending/confirmed order is cancelled, reservation released, and paid value becomes refund due | Dependencies: UC-12–13. Acceptance: allowed/forbidden states, release movement, paid/late refund-due state. Backlog outcome: Eligible Customer cancellation.
UC-17 | Staff order enquiry | E / B | Staff/Manager | View and Search Sales Orders | Proposed | W5 | P0 / Medium / 2 pts | Operator searches all channels and lifecycle states by business criteria | Dependencies: UC-12, UC-29 fixtures. Acceptance: role guard, channel/status/date filters, actionable preset, bounded stable paging. Backlog outcome: Staff/Manager sales-order search.
UC-18 | Staff order enquiry | E / C | Staff/Manager | View Sales Order Detail | Proposed | W5 | P0 / Medium / 2 pts | Operator sees operational, stock, payment, return, receipt, audit, and allowed actions | Dependencies: UC-17, ledgers. Acceptance: projection without duplication; Staff/Manager action differences. Backlog outcome: Operational order detail/actions.
UC-19 | Product administration | B / D | Manager | Manage Product Classification Data | Proposed | W3 | P1 / Medium / 2 pts | Manager maintains Category and Brand reference data in one workspace | Dependencies: UC-02 Manager. Acceptance: normalized uniqueness; referenced-active deactivation conflict. Backlog outcome: Category/Brand workspace.
UC-20 | Product administration | B / D | Manager | Manage Product Catalogue and SKUs | Proposed | W3 | P0 / High / 3 pts | Manager maintains product content and manually defined sale units/SKUs with price, threshold, and active state | Dependencies: UC-19. Acceptance: activation invariants, immutable SKU code/history, stale version conflict. Backlog outcome: Product/SKU workspace.
UC-21 | Inventory enquiry | D / B | Staff/Manager | View Inventory Overview | Proposed | W3 | P0 / Medium / 2 pts | Operator searches on-hand, reserved, available, and low-stock SKU balances | Dependencies: UC-20. Acceptance: on-hand/reserved/available, low-stock, inactive-stock discoverability. Backlog outcome: Current inventory overview.
UC-22 | Inventory receiving | D / C | Staff/Manager | Receive Stock | Proposed | W6 | P0 / High / 3 pts | Operator records one external delivery and atomically increases its SKU balances | Dependencies: UC-20–21. Acceptance: multi-line balance/movement tie-out, rollback, retry/fingerprint conflict. Backlog outcome: Atomic stock receipt.
UC-23 | Inventory correction | D / C | Manager | Adjust Stock | Proposed | W6 | P0 / Medium / 2 pts | Manager records a reasoned non-zero correction without violating reservations | Dependencies: UC-21. Acceptance: Manager/reason/version/nonnegative/reservation guards and one movement. Backlog outcome: Guarded stock adjustment.
UC-24 | Inventory audit | D / C | Manager | View Stock Movement History | Proposed | W6 | P1 / Medium / 2 pts | Manager inspects immutable physical/reservation movements by SKU/order/reference | Dependencies: all stock-changing UCs. Acceptance: filters, stable paging, business-reference trace, no edit/delete. Backlog outcome: Immutable movement history.
UC-25 | Fulfillment | E / D | Staff/Manager | Pack Confirmed Order | Proposed | W5 | P0 / Low / 1 pts | Eligible confirmed order becomes packing with actor/time history | Dependencies: UC-17–18. Acceptance: guarded single transition/history; zero stock delta. Backlog outcome: Confirmed order packing.
UC-26 | Fulfillment | E / D | Staff/Manager | Dispatch Order for Delivery | Proposed | W5 | P0 / High / 3 pts | Eligible packed order leaves stock and becomes shipping | Dependencies: UC-25. Acceptance: order-then-SKU lock, exact physical/reserve deltas, duplicate guard. Backlog outcome: Packed order dispatch.
UC-27 | Fulfillment | E / C | Staff/Manager | Record Delivery Outcome | Proposed | W6 | P0 / High / 3 pts | Shipping order becomes completed after success or terminal delivery-failed after returned failure | Dependencies: UC-26. Acceptance: exact COD collection or restored stock; terminal duplicate/race tests. Backlog outcome: Delivery success/returned failure.
UC-28 | Store cancellation | C / E | Manager | Cancel Order by Store | Proposed | W7 | P0 / High / 3 pts | Manager cancels an allowed pre-shipping order with reason, stock release, and refund-due result | Dependencies: UC-18, payment/stock ledgers. Acceptance: reason/state/role guards, reservation release, refund-due projection. Backlog outcome: Manager pre-shipping cancellation.
UC-29 | Counter sales | D / C | Staff/Manager | Sell Products at Counter | Proposed | W6 | P0 / High / 3 pts | One atomic command creates a completed cash sale, collection, stock movements, and receipt | Dependencies: UC-20–21, ledgers. Acceptance: last-unit race, retry, full rollback, cash/stock/order reconciliation. Backlog outcome: Atomic cash counter sale.
UC-30 | Customer returns | B / E | Customer | Request Return for Own Order | Proposed | W8 | P1 / High / 3 pts | Customer creates the one allowed item/quantity request for an eligible owned DELIVERY order | Dependencies: UC-15, completed DELIVERY order. Acceptance: owner/deadline/reason/line caps, one request, retry conflict. Backlog outcome: Owned Customer return request.
UC-31 | In-store returns | D / E | Staff/Manager | Create In-Store Return Request | Proposed | W8 | P1 / High / 3 pts | Operator creates the one allowed item/quantity request after validating receipt/order evidence | Dependencies: UC-18/29, completed order. Acceptance: receipt evidence, either sale channel, line caps, duplicate guard. Backlog outcome: Receipt-based in-store request.
UC-32 | Return decision | E / B | Manager | Review Return Request | Proposed | W8 | P1 / Medium / 2 pts | Manager approves the complete eligible request or rejects it with reason | Dependencies: UC-30–31. Acceptance: Manager-only approve-all/reject, reason, stale/duplicate behavior. Backlog outcome: Whole-request Manager decision.
UC-33 | Return receiving | E / D | Staff/Manager | Receive and Inspect Returned Items | Proposed | W8 | P1 / High / 3 pts | Operator performs one intake, records disposition quantities, and restores sellable stock | Dependencies: UC-32. Acceptance: positive receipt, disposition equation, sellable movement, no second intake. Backlog outcome: One physical return intake.
UC-34 | Refund management | C / E | Manager | Record Refund Completion | Proposed | W8 | P1 / High / 3 pts | Manager records actual eligible money returned for a cancellation/failure/received return without exceeding cap | Dependencies: UC-16/27/33, money ledger. Acceptance: source eligibility, exact remaining cap, duplicate and atomic state tests. Backlog outcome: Actual capped refund completion.
UC-35 | Reporting | C / B | Manager | View Cash Movement Report | Proposed | W8 | P1 / High / 3 pts | Manager sees collections, refunds, and net cash movement by transaction date/method | Dependencies: complete money ledger. Acceptance: half-open transaction dates; collection-refund-net independent tie-out. Backlog outcome: Cash movement report.
UC-36 | Reporting | B / C | Manager | View Sales Performance Report | Proposed | W8 | P1 / High / 3 pts | Manager sees completed sales volume/value/channel/product demand by completion date | Dependencies: completed order snapshots. Acceptance: completion cohort, channels/payment dimensions, item sum tie-out. Backlog outcome: Gross completed-sales report.
UC-37 | Reporting | D / C | Manager | View Inventory Roll-Forward Report | Proposed | W8 | P1 / High / 3 pts | Manager sees opening balances plus period deltas reconciling to closing balances | Dependencies: complete movement ledger. Acceptance: opening + categorized deltas = closing, boundary and seed tests. Backlog outcome: Inventory roll-forward report.
TECH-01 | Platform Foundation | A + all review | Team | Repository and GitLab foundation | Proposed | W1 | Cross-cutting task | GitLab monorepo, Java/Node versions, ignored env sample, protected `main`, MR templates | Not an actor-goal use case. Evidence must come from GitLab, tests, RDS/SDS, or a repeatable demo as applicable.
TECH-02 | Platform Foundation | A + C | Team | Session and CSRF walking skeleton | Proposed | W2 | Cross-cutting task | Spring Security session/CSRF walking skeleton; React login/mutation/logout/fresh-token smoke | Not an actor-goal use case. Evidence must come from GitLab, tests, RDS/SDS, or a repeatable demo as applicable.
TECH-03 | Platform Foundation | D + C | Team | PostgreSQL and Flyway foundation | Proposed | W2 | Cross-cutting task | Supabase-aligned CI PostgreSQL; Flyway `app`; Hibernate validate; safe first-Manager bootstrap | Not an actor-goal use case. Evidence must come from GitLab, tests, RDS/SDS, or a repeatable demo as applicable.
TECH-04 | Platform Foundation | B | Team | React and Spring build integration | Proposed | W2 | Cross-cutting task | Vite development proxy and production React build served from Spring artifact | Not an actor-goal use case. Evidence must come from GitLab, tests, RDS/SDS, or a repeatable demo as applicable.
TECH-05 | Platform Foundation | A | Team | Shared API conventions | Proposed | W2 | Cross-cutting task | Stable API problem/error, paging, validation, correlation-ID, and DTO conventions | Not an actor-goal use case. Evidence must come from GitLab, tests, RDS/SDS, or a repeatable demo as applicable.
TECH-06 | Platform Foundation | C + D | Team | PostgreSQL concurrency harness | Proposed | W4 | Cross-cutting task | PostgreSQL concurrency harness and global aggregate/SKU lock-order proof | Not an actor-goal use case. Evidence must come from GitLab, tests, RDS/SDS, or a repeatable demo as applicable.
TECH-07 | Platform Foundation | C | Team | Online payment provider foundation | Proposed | W7 | Cross-cutting task | Provider adapter, signed callback/IPN, fixed Clock, 15-minute expiry scheduler proof | Not an actor-goal use case. Evidence must come from GitLab, tests, RDS/SDS, or a repeatable demo as applicable.
DATA-01 | Data & Demo | B coordinates | Team | Vietnamese demo data | Proposed | W3 onward | Cross-cutting task | Credible Vietnamese seed catalogue; all leads add their owned lifecycle fixtures | Not an actor-goal use case. Evidence must come from GitLab, tests, RDS/SDS, or a repeatable demo as applicable.
QA-01 | Quality Assurance | feature lead | Team | Continuous feature verification | Proposed | every MR | Cross-cutting task | Unit/controller/PostgreSQL/React tests plus browser smoke where applicable | Not an actor-goal use case. Evidence must come from GitLab, tests, RDS/SDS, or a repeatable demo as applicable.
DOC-01 | Requirements & Traceability | feature lead | Team | RDS and traceability maintenance | Proposed | W1–8 | Cross-cutting task | RDS and traceability change in same MR as behavior change | Not an actor-goal use case. Evidence must come from GitLab, tests, RDS/SDS, or a repeatable demo as applicable.
DOC-02 | Requirements & Traceability | rotating auditor | Team | Feature-freeze drift audit | Proposed | W9 | Cross-cutting task | ID/name/actor/state/API/schema/test drift report is empty at feature freeze | Not an actor-goal use case. Evidence must come from GitLab, tests, RDS/SDS, or a repeatable demo as applicable.
SDS-01 | Software Design Specification | all, one editor | Team | SDS from verified implementation | Proposed | W9–10 | Cross-cutting task | Actual symbol/query/migration/test inventory from tagged commit; no planned fake classes | Not an actor-goal use case. Evidence must come from GitLab, tests, RDS/SDS, or a repeatable demo as applicable.
REL-01 | Release | all | Team | Clean release reproduction | Proposed | W9 | Cross-cutting task | Fresh clone -> migrate -> seed -> test -> package -> run on clean environment | Not an actor-goal use case. Evidence must come from GitLab, tests, RDS/SDS, or a repeatable demo as applicable.
DEMO-01 | Demo & Defense | all | Team | Core demo and defense rehearsal | Proposed | W9–10 | Cross-cutting task | Four core paths plus selected conflict/race/external-failure paths are repeatable | Not an actor-goal use case. Evidence must come from GitLab, tests, RDS/SDS, or a repeatable demo as applicable.

## Contribution
Name | Role | Tasks/Modules Assigned | Contribution %
ChuanDH | Member | Chưa chốt; gán Lead A–E sau R1 walking skeleton | 20%
ThienTP | Member | Chưa chốt; gán Lead A–E sau R1 walking skeleton | 20%
AnNP | Member | Chưa chốt; gán Lead A–E sau R1 walking skeleton | 20%
NhaLP | Member | Chưa chốt; gán Lead A–E sau R1 walking skeleton | 20%
TranLTB | Member | Chưa chốt; gán Lead A–E sau R1 walking skeleton | 20%